## Jan-June
ANNEX B |  | ANNEX A
Philippine Ports Authority - Port Management Office of NCR North Procurement Monitoring Report as of January - June 2025 |  | Department of Budget and Management Annual Procurement Plan for FY 2006
Code (PAP) PR No. | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing/P.O | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Accept
Completed Procurement Activities
NH-9449-25 | Supply and Delivery of A3 Size Picture with Frame | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-05-14 | N/A | 2025-05-19 | 2025-06-30 | GOP | 14000 | 14000 | 0 | 14000 | 14000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9450-25 | Supply and Delivery of Truckmaster Engine Battery Low Maintenance, 2D/N120L/F51L for VTMS Control Center | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-05-07 | N/A | 2025-05-23 | 2025-05-26 | GOP | 23000 | 23000 | 0 | 17414 | 17414 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9463-25 | Procurement of Aircon repair and replacement of spare parts (If necessary) including labor cost for Hyundai Starex Year Model 2010 with Plate No. NOW-832 | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-05 | N/A | 2025-05-09 | 2025-05-09 | GOP | 22000 | 22000 | 0 | 22000 | 22000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9465-25 | Supply and Delivery of Various Materials for Internet Connection at RMD Finance | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-23 | N/A | 2025-04-29 | 2025-04-30 | GOP | 10000 | 10000 | 0 | 8600 | 8600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9466-25 | Supply and Delivery of LED Bulb, Outdoor Globe Lamp and Outdoor Lighting Reflector | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-23 | N/A | 2025-04-29 | 2025-04-30 | GOP | 13860 | 13860 | 0 | 12060 | 12060 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9486-25 | Supply and Delivery of three (3) units of All-in-One Ink Tank Printer | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-05-05 | N/A | 2025-05-14 | 2025-05-14 | GOP | 30000 | 30000 | 0 | 26400 | 26400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9491-25 | Supply and Delivery of Various Cleaning Materials for Motor Vehicles | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-05-07 | N/A | 2025-05-15 | 2025-05-19 | GOP | 20000 | 20000 | 0 | 19436 | 19436 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9494-25 | Supply and Delivery of Speaker | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-16 | N/A | 2025-06-16 | 2025-06-16 | GOP | 46000 | 46000 | 0 | 39100 | 39100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9495-25 | Supply and Delivery of Various Medical Supplies for 1st Semester | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-29 | N/A | 2005-05-29 | 2005-05-29 | GOP | 37000 | 37000 | 0 | 29056 | 29056 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9496-25 | Supply and Delivery of Various Office Supplies for 1st Quarter of CY 2025 | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-03-25 | N/A | N/A | 2025-03-31 | 2025-04-02 | N/A | 2025-04-02 | 2025-04-10 | N/A | 2025-05-29 | 2025-05-29 | GOP | 255689.52 | 255689.52 | 0 | 247852 | 247852 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9516-25 | Supply and Delivery of Mop Squeezer | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-28 | N/A | 2025-05-30 | 2025-05-30 | GOP | 5000 | 5000 | 0 | 4400 | 4400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9517-25 | Supply, Delivery and Services of 600 containers per month (5-gals, per round container of Purified Drinking Water for a period of seven (7) months | [19 empty] | PMO-NCR North | Sec. 35.3 Take-Over of Contracts | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | N/A | N/A | GOP | 236629 | 236629 | 0 | 168000 | 168000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9542-25 | Supply and Delivery of Wireless Network Routers, Switch Hub and other materials for VTMS Control Center Manila, TMO-Vitas Pier 18 and Manila Multipurpose Terminal (R-II) | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-05-05 | N/A | 2025-05-19 | 2025-05-20 | GOP | 20600 | 20600 | 0 | 12800 | 12800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9552-25 | Supply and Delivery of File Storage Boxes | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-02 | N/A | 2026-05-22 | 2026-05-22 | GOP | 55000 | 55000 | 0 | 12360 | 12360 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9553-25 | Supply and Delivery of Custom Magazine File Box | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-02 | N/A | 2026-05-22 | 2026-05-22 | GOP | 28500 | 28500 | 0 | 9560 | 9560 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9554-25 | Supply and Delivery of Continuous Form | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-04-30 | N/A | N/A | 2025-05-09 | 2025-05-16 | N/A | 2025-05-20 | 2025-05-27 | N/A | 2025-05-29 | 2025-05-29 | GOP | 120000 | 120000 | 0 | 59820 | 59820 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9556-25 | Supply and Delivery of Lever Arch File A3 Size | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-02 | N/A | 2026-05-22 | 2026-05-22 | GOP | 28500 | 28500 | 0 | 9760 | 9760 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9559-25 | Supply and Delivery of Various Consumables Supplies at Radar Station 2 Corregidor for 1st Semester CY 2025 | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-04-30 | N/A | N/A | 2025-05-09 | 2025-05-20 | N/A | 2025-05-22 | 2025-05-23 | N/A | 2025-05-27 | 2025-05-27 | GOP | 99000 | 99000 | 0 | 82100 | 82100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9597-25 | Supply and Delivery of Janitorial Supplies for 2nd Quarter of CY 2025 | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-28 | N/A | 2025-05-30 | 2025-05-30 | GOP | 85227 | 85227 | 0 | 84086 | 84086 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Allotted Budget of Procurement Activities | [35 empty] | 1150005.52
Total Contract Price of Procurement Activities Conducted | [35 empty] | 878804
Total Savings(Total Alloted Budget - Total Contract Price | [35 empty] | 271201.52
On-Going Procurement Activities
NH-9453-25 | Supply and Delivery of Motorcycle Gear Accessories | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  |  | GOP | 14000 | 14000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9457-25 | Procurement of LED Warning Light 10-30 Volts | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-19 | N/A | 2025-06-19 |  | GOP | 11520 | 11520 | 0 | 10500 | 10500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9492-25 | Supply and Delivery of Cabinets | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-04-22 | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-20 | 2025-07-07 | N/A | 2025-07-09 | 2025-07-19 | GOP | 200000 | 200000 | 0 | 89600 | 89600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9493-25 | Supply and Delivery of Laminating Machine | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  |  | GOP | 25000 | 25000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9555-25 | Supply and Delivery of PPA Letterhead | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  |  | GOP | 50000 | 50000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9557-25 | Supply and Delivery of Digital Blood Pressure Monitor | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  |  | GOP | 20000 | 20000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9570-25 | Supply and Delivery of Tires for Toyota Commuter (2024) with Plate no. SND-2264, Toyta Hi-Lux (2024) with Plate no. SND-2280 and Toyota Grandia (2017) with Plate No. SAB-4357 | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-30 | N/A | 2025-06-20 | 2025-06-25 | N/A |  |  | GOP | 125000 | 125000 | 0 | 83325 | 83325 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9579-25 | Supply and Delivery of Various Office Supplies for 2nd Quarter 2025 | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | N/A | N/A | 2025-06-09 |  | N/A |  |  | GOP | 376295.8 | 376295.8 | 0 | 343608 | 343608 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9580-25 | Supply and Delivery of Marine LogBook | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-16 | N/A |  |  | GOP | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9596-25 | Supply and Delivery of 3SMF Battery for Toyota Hilux Year Model 2013 with Plate No. POJ-331 | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-19 | N/A | 2025-06-19 |  | GOP | 10000 | 10000 | 0 | 7130 | 7130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9611-25 | Supply and Delivery of Tubeless Tires 215/70 R16C for Hyundai Starex Year Model 2018 with Plate No. NBC-6114 including Tire Mounting and Tire Balancing | [19 empty] | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-25 | N/A | 2025-06-28 |  | GOP | 54000 | 54000 | 0 | 43645 | 43645 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9624-25 | Procurement of Service for the Inspection and Repair of One (1) Unit Eaton Fire Alarm System at the VTMS Control Center Building, MICT, Tondo Manila | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | [9 empty] | GOP | 80000 | 80000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9625-25 | Procurement of Service of Monthly Preventive Maintenance of Kone Elevator in VTMS Control Center | [19 empty] | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | [9 empty] | GOP | 65000 | 65000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Allotted Budget of Procurement Activities | [35 empty] | 1060815.8
Total Contract Price of Procurement Activities Conducted | [35 empty] | 607808
Total Savings(Total Alloted Budget - Total Contract Price | [35 empty] | 453007.8
0
| Prepared by: | [22 empty] | Reviewed by: | [8 empty] | Recommending Approval: | [9 empty] | Noted by:
| JEYMER M. SELOSA | DEFINITION | [17 empty] | Remarks |  |  |  | MARISA T. ARIMADO | [8 empty] | FRANCIS ALDRICH A. RUBIO | [9 empty] | JENNELIZA D. REBONG
| BAC , Support Staff | 1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [21 empty] | BAC Secretariat, Head | [8 empty] | BAC-NCRN Chairperson | [9 empty] | Port Manager / Head of Procuring Entity
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evaluation; post qualification; award of contract; contract preparation), Delivery/Acceptance Process, Payment Process
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
|  | 7. ABC - Approved Budget for the Contract | [17 empty] | Breakdown into mooe and co for tracking purposes; alligned with budget documents
|  | 8. Remarks - brief description of program or project | [17 empty] | Any remark that will help GPPB track programs and projects

## Jul - Dec
ANNEX B
Philippine Ports Authority - Port Management Office of NCR North Procurement Monitoring Report as of July-December 2025
Code (PAP) PR No. | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds |  | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP) |  |  | PAYMENTS
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | P.O # | Contract Signing/P.O | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | SUPPLIER | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Accept
Completed Procurement Activities
NH-9847-25 | 3-pcs. CZ Riso Ink CZ type S-4877 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-22 | 12-05-25 | 2025-11-05 | N/A | 2025-12-05 | 2025-12-05 | GOP | Copylandia Office Systems Corp. | 6000 | 6000 | 0 | 4005 | 4005 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9909-25 | Procurement of 8-pcs. 200W Flood Lights for Exterior Port Lighting, ESD | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-12 |  | N/A | N/A | 2025-12-17 | 2026-01-06 | GOP | Ace Hardware Phils. Inc. | 43992 | 43992 | 0 | 43992 | 43992 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9927-25 | Procurement of 1-pc. Automotive Battery, 3SMF, 12V, for Genset located at NCRN Admin Bldg. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GOP |  | 9000 | 9000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9951-25 | PROCUREMENT OF HANDSOAP DISPENSER AND TISSUE HOLDER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-22 | GOP | Ace Hardware Phils. Inc. | 13000 | 13000 | 0 | 7088.75 | 7088.75 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9925-25 | PROCUREMENT OF MEDIA CONVERTER FOR VTMS CONTROL CENTER AND RS1-IPB | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP |  | 4000 | 4000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF ONE (1) PC KEYBOX HOLDER TO BE USED AT PMO NCR NORTH LOBBY | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-20 | N/A | N/A | N/A | 2025-09-02 | GOP | Ace Hardware Phils. Inc. | 3000 | 3000 | 0 | 2128.52 | 2128.52 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF ONE (1) UNIT OF UPS 650 VA, ONE (1) PC SURGER PROTECTOR AND FIVE (5) UNITS OF 4 PORT HUB TO BE USED BY COA PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | N/A | N/A | N/A | 2025-10-21 | GOP | PC Express / Ugreen | 9300 | 9300 | 0 | 9059 | 9059 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF CALLING CARD FOR USED OF THE PORT MANAGER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-12 | GOP | Pinagpala Printing Press | 3000 | 3000 | 0 | 1425 | 1425 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF FIFTEEN (15) PCS OF CERTIFICATE FRAMES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | GOP | National Bookstore | 2000 | 2000 | 0 | 1950 | 1950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9945-25 | Procurement of Floor Matting to be used at PMO NCR North Lobby | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2025-12-31 | - | GOP | Ban Bee Comm'l Co., Inc. | 12000 | 12000 | 0 | 10194.9 | 10194.9 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF FOURTEEN (14) PCS OF CUSTOMIZED A3 FRAME FOR ORGANIZATIONAL CHART | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | N/A | N/A | N/A | 2025-08-02 | GOP |  | 14000 | 14000 | 0 | 13300 | 13300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9699-25 | PROCUREMENT OF ONE (1) PAIR OF SAFETY SHOES TO USED BY THE PORT MANAGER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-31 | GOP |  | 3500 | 3500 | 0 | 1817.36 | 1817.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | Supply & Delivery of 2-units Radiator Assembly and 1-Water Pump Assembly for RS-2 15KVA Genset | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | - | - | GOP | Zayne Medfical Supplies | 210000 | 210000 | 0 | 198056.32 | 198056.32 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9920-25 | Supply & Delivery of 4-pcs. Yokohama Tires, 265/665 R17, for T. Hi-Lux Mobile Patrol, NBH-6409, PPD | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | - | GOP | Grandmah;e Corporation | 60000 | 60000 | 0 | 62000 | 62000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9742-25 | SUPPLY AND DELIVERY OF 3 UNIT FIRE HOSE CABINET WITH 100-FT FIRE HOSE DOUBLE JACKET | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-15-25 | N/A | N/A | 2025-12-29 | - | GOP | Tigronyx Fire Safety Inc. | 52500 | 52500 | 0 | 31470 | 31470 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF ONE (1) UNIT OF CALCULATOR 14 DIGITS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-29 | GOP | Ban Bee Comm'l Co., Inc. | 1000 | 1000 | 0 | 850 | 850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9132-25 | Procurement of Scanner, Printers and Dot Matrix Printers, for Various NCRN Office Use | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 |  | 2025-12-11 | N/A | 2015-12-13 | 2026-01-06 | GOP | URQUAN INC. | 145000 | 145000 | 0 | 134210 | 134210 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9136-25 | Supply & Delivery of 1-pc. 3SMF N70 Engine Battery, for use at T. Hi-Lux, Plate No. SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-18 | N/A | 2025-12-18 | 2025-01-05 | GOP | MarkPower Enterprises | 8000 | 8000 | 0 | 6800 | 6800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9457-25 | Procurement of LED Warning Light 10-30 Volts | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 |  | 2025-06-19 | N/A | 2025-06-19 | 2025-07-01 | GOP | Grandmah;e Corporation | 11520 | 11520 | 0 | 10500 | 10500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9492-25 | Supply and Delivery of Cabinets | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-04-22 | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-20 |  | 2025-07-07 | N/A | 2025-07-09 | 2025-07-19 | GOP | GOP | 200000 | 200000 | 0 | 89600 | 89600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9569-25 | Supply and Delivery of Batteries for Various Motor Vehicles | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 |  | 2025-06-05 | N/A | 2025-06-19 | 2025-06-20 | GOP | Batparts Supply Co., Inc. | 86000 | 86000 | 0 | 52021 | 52021 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9570-25 | Supply and Delivery of Tires for Toyota Commuter (2024) with Plate no. SND-2264, Toyta Hi-Lux (2024) with Plate no. SND-2280 and Toyota Grandia (2017) with Plate No. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-30 | N/A | 2025-06-20 |  | 2025-06-25 | N/A | 2025-06-29 | 2025-07-01 | GOP | Tire Asia Group Inc. | 125000 | 125000 | 0 | 83325 | 83325 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9579-25 | Supply and Delivery of Various Office Supplies for 2nd Quarter of CY 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | N/A | N/A | 2025-06-09 |  | 2025-07-09 | N/A | 2025-07-31 | 2025-08-01 | GOP | Mostaco Mktg. | 376295.8 | 376295.8 | 0 | 343608 | 343608 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2
NH-9580-25 | Supply and Delivery of Marine LogBook | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 |  | 2025-06-16 | N/A | 2025-07-04 | 2025-07-07 | GOP | Ban Bee Comm'l Co., Inc. | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 5
NH-9596-25 | Supply and Delivery of 3SMF Battery for Toyota Hilux Year Model 2013 with Plate No. POJ-331 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 |  | 2025-06-19 | N/A | 2025-06-19 | 2025-07-01 | GOP | 10000 | 10000 | 10000 | 0 | 7130 | 7130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9611-25 | Supply and Delivery of Tubeless Tires 215/70 R16C for Hyundai Starex Year Model 2018 with Plate No. NBC-6114 including Tire Mounting and Tire Balancing | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 |  | 2025-06-25 | N/A | 2025-06-28 | 2025-07-01 | GOP | Tire Asia Group Inc. | 54000 | 54000 | 0 | 43645 | 43645 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9617-25 | Procurement of 1-unit All In One Desktop Computer, for use of COA | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 09-17-25 | 2025-06-27 | N/A | 2025-07-30 | 2025-08-14 | GOP | Masangkay Computer Center | 50000 | 50000 | 0 | 49998 | 49998 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9624-25 | PROCUREMENT OF SERVICE FOR THE INSPECTION AND REPAIR OF ONE (1) UNIT EATON FIRE ALARM SYSTEM AT THE VTMS CONTROL CENTER BUILDING, MICT, TONDO MANILA | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-07-03 | N/A | N/A | 2025-07-18 | 2025-07-30 | 2025-07-30 | 2025-08-13 | 12-03-25 | 2025-08-22 | N/A | 2025-08-24 | 2025-12-09 | GOP | Iptek Comm. Co. Ltd. | 80000 | 80000 | 0 | 75000 | 75000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9625-25 | Procurement of Service of Monthly Preventive Maintenance of Kone Elevator in VTMS Control Center | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP |  | 65000 | 65000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
NH-9647-25 | Supply and Delivery of Submersible Water Pump | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 |  | 2025-08-04 | N/A | 2025-08-11 | 2025-08-14 | GOP | Sonitram Mdsg Corp. | 15000 | 15000 | 0 | 11800 | 11800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9660-25 | Supply, Delivery and Installation of 1HP Window Type Aircondition Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | 2025-12-14 | N/A | N/A | 2025-12-19 | 2025-12-23 | N/A | 2025-12-22 |  | 2025-12-29 | N/A | 2025-12-29 | - | GOP | O Plus | 64000 | 64000 | 0 | 92396 | 92396 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9676-25 | Supply & Delivery of Phil., Flag, DOTr & PPA Flag, for use at NCRN Offices | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | 11-03-25 | 2025-07-31 | N/A | 2025-10-10 | 2025-10-10 | GOP | Atlas Super Flags | 47400 | 47400 | 0 | 35400 | 35400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9678-25 | Procurement of 450-pcs. Sacks, 50kls capacity, for use at NCRN Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | 09-17-25 | 2025-07-31 | N/A | 2025-08-01 | 2025-08-14 | GOP | AE Samonte Mdse. | 11250 | 11250 | 0 | 8325 | 8325 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9679-25 | Procurement of Whiteboards | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 |  | 2025-07-31 | N/A | 2025-08-07 | 2025-08-14 | GOP | AE Samonte Mdse. | 34400 | 34400 | 0 | 33650 | 33650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9680-25 | Supply & Dedlivery of Assorted Trashbins, for IMS Compliance | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-08-12 | N/A | N/A | 2025-09-08 | 2025-09-08 | N/A | 2025-09-29 | 12-03-25 | 2025-10-08 | N/A | 2025-11-17 | 2025-11-19 | GOP | Abeltrade Ent. Corp. | 214000 | 214000 | 0 | 140885 | 140885 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9700-25 | Procurement of Various LED Lights for the Buidings & Office of NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 170000 | 170000 | 0 | 160320 | 160320 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9702-25 | Procurement of Metal Works & Various Construction Equipment for In-House Routinary R&M of Buildings at NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 86450.1 | 86450.1 | 0 | 86430 | 86430 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9703-25 | Procurement of Various Electrical Materials for Buildings & Offices at NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 85344 | 85344 | 0 | 85312 | 85312 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9714-25 | Procurement of Service for Mobilization of Flr Mounted ACU, from Annex Bldg. to VTMS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-29 | 12-05-25 | 2025-10-13 | N/A | 2025-10-15 | 2025-12-24 | GOP | AVF Airconditioning Center | 26000 | 26000 | 0 | 24300 | 24300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9715-25 | Procurement of Service for Leak Repair & Reprocessing of ACU, TMO Vitas | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 | 12-05-25 | 09-30-25 | N/A | 2025-10-15 | 2025-11-24 | GOP | AVF Airconditioning Center | 14500 | 14500 | 0 | 13800 | 13800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9718-25 | Procurement of Furnitures, for use at the Office of the PM Waiting Area | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-21 |  | 2025-11-12 | N/A | 2025-11-12 | 2025-12-05 | GOP | Casamia Furniture Center, Inc. | 75000 | 75000 | 0 | 73465 | 73465 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9738-25 | Supply and Delivery of Various Safety and Health Signages | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 |  | 2025-10-14 | N/A | 2025-10-14 | 2025-10-28 | GOP | Jarin Art Sign & Gen. Mdse | 15000 | 15000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9739-25 | Supply & Delivery of Various Personal Protective Equipment (PPE) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 09-17-25 |  | 2025-11-13 | N/A | 2025-10-22 | 2025-12-22 | GOP | Hi-Safety Industrial Supplies Inc. | 75000 | 7500 | 0 | 35781.24 | 35781.24 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9740-25 | Supply & Delivery of Fireman Suit Cabinet, for IMS & BFP Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 | 12-03-25 | 2025-10-23 | N/A | 2025-10-27 | 2025-10-29 | GOP | Realsan Enterprises | 5000 | 50000 | 0 | 46000 | 46000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9741-25 | Supply & Delivery of Bokashi Compost Bins, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11-26-25 |  | N/A | N/A | 1941-01-24 | 1936-12-16 | GOP | Jarin Art Sign & Gen. Mdse | 15000 | 15000 | 0 | 13500 | 13500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9743-25 | Supply & Delivery of ABC and HCFC Fire Extinguisher | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-09-19 | N/A | N/A | 2025-10-29 | N/A | N/A | 2025-11-04 |  | N/A | N/A | 2025-12-05 | 2025-12-22 | GOP | ES Castro Trading | 295000 | 295000 | 0 | 72000 | 72000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9744-25 | Supply & Delivery of Various Oil Spill Recovery Materials, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-29 | 12-03-25 | 2025-10-14 | N/A | 2025-10-28 | 2025-10-28 | GOP | 30000 | 48100 | 48100 | 0 | 48100 | 48100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9775-25 | Supply, Delivery & Services of 600-Containers of Purified Drinking Water for twelve (12) months (Nov. 2025 to Oct. 2026) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-13 | N/A | N/A | 2025-10-24 | 2025-10-29 | 2025-10-29 | 2025-10-29 | N/A | 2025-10-30 | 2025-10-30 | N/A | N/A | GOP | Maris Pure Corp. | 314400 | 314400 | 0 | 314400 | 314000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9784-25 | Supply & Delivery of Various Office Supplies for the 3rd Qtr. 2025 | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | 2025-10-02 | 2025-10-02 | 2025-10-02 | N/A | N/A | 2025-10-02 | 11-07-25 | 2025-10-08 | N/A | 2025-10-16 | 2025-10-28 | GOP | Mostaco Mktg. | 310748.25 | 310748.25 | 0 | 308000 | 308000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 3
NH-9810-25 | Supply & Delivery of Janitorial Supplies for the 4th Qtr. 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-23 | 11-07-25 | N/A | N/A | 2025-12-29 |  | GOP | Kenleen Intl. Distribution, Inc. | 85227 | 85227 | 0 | 78082 | 78082 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9812-25 | Supply and Dellivery of Digital Blood Pressure Monitor, for use at Various NCRN Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-01 | 11-07-25 | 2025-10-20 | N/A | 2025-10-22 | 2025-10-28 | GOP | Aspire Appliance Marketing | 23000 | 23000 | 0 | 20216 | 20216 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9818-25 | PROCUREMENT OF ALTERNATOR ASSEMBLY FOR MITSUBISHI ADVENTURE YEAR MODEL 2013 WITH PLATE NO. SLG-382 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-11 | GOP | Richland Autosupply | 10000 | 10000 | 0 | 9800 | 9800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9839-25 | Maintenance of VTMS Radar Station 1 Facility at MICT, Tondo, Manila (MFP-NCN-04-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | 2025-12-01 | 2025-12-01 | 2025-12-09 | N/A | N/A | GOP | Big J Steel Construction Corp. | 983160 | 983160 | 0 | 963496.8 | 963496.8 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9840-25 | Maintenance of PMO NCR North Port Police Bldg., North Harbor, Tondo, Manila (MFP-NCN-02-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | N/A | N/A | GOP | Big J Steel Construction Corp. | 894950 | 894950 | 0 | 870202.5 | 870202.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9841-25 | Maintenance of PMO NCR North Annex Bldg. and Main Entrance Gate at North Harbor, Tondo, Manila (MFP-NCN-03-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | N/A | N/A | GOP | Big J Steel Construction Corp. | 997102 | 997102 | 0 | 969482.27 | 969482.27 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9842-25 | Maintenance of PMO NCR North Admin. Bldg. Including Access Bridgeway at North Harbor, Tondo, Manila (COP-MFP-NCN-01-25) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | N/A | N/A | GOP | Big J Steel Construction Corp. | 996638 | 996638 | 0 | 976997.98 | 976997.98 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9843-25 | Supply & Delivery of 10-bxs Toner Cartridge W1002YC for HP Photocopier Model E2630DN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-21 |  | N/A | N/A | 2025-12-22 | 2026-01-05 | GOP | Data Images Pluls Automation Phils, Inc. | 80000 | 80000 | 0 | 66000 | 66000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9843-25 | Procurement of Degreaser to be used by Admin-GSU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12-19-25 |  | N/A | N/A | 2025-12-19 | 2026-01-05 | GOP | Kenleen Intl. Distribution Inc. | 8000 | 8000 | 0 | 4960 | 4960 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9859-25 | PROCUREMENT OF BRAKE SHOE, BRAKE MASTER ASSEMBLY AND BRAKE PAD FOR TOYOTA GRANDIA YEAR MODEL: 2017 WITH PLATE NO. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-05 | GOP | EDCM Auto Supply | 14500 | 14500 | 0 | 13775 | 13775 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9860-25 | Procurement of Power Steering Pump Assembly, for Hyundai Grand Starex, Model 2018, Plate no. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-08 | N/A | 2025-12-18 | 2025-01-05 | GOP | MarkPower Enterprises | 17000 | 17000 | 0 | 16800 | 16800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9862-25 | Supply & Delivery of Various Medical Supplies for Second Semester 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-11 | N/A | 2025-12-23 | 2026-01-06 | GOP | BND Pharma and Medical Supplies Distribution Corp. | 37000 | 37000 | 0 | 28559.7 | 28559.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9867-25 | Procurement of Service for Refill and Reconditioning of Fire Extinguishers | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-11-05 | N/A | N/A | 2025-11-12 | N/A | N/A | 2025-11-24 |  | 2025-12-01 | N/A | 2025-12-16 | 2025-12-22 | GOP | ES Castro Trading | 55250 | 55250 | 0 | 28500 | 28500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9868-25 | PROCUREMENT OF ONE (1) PC DIFFUSER OIL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-30 | GOP | Scentsmith Perfumery Inc. | 1000 | 1000 | 0 | 998 | 998 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9873-25 | TIRE ALIGNMENT AND CAMBER CORRECTION OF TOYOTA GRANDIA WITH PLATE NO. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-07 | GOP | Nes Tire Supply | 4000 | 4000 | 0 | 1200 | 1200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9879-25 | Procurement of Various Construction Materials, for Plumbing & Masonry Works for In-House Routinary R&M of Buildings & Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-21 |  | 2025-11-28 | N/A | 2025-12-16 | 2025-12-16 | GOP | Boston Builder's Center | 156159.65 | 156159.65 | 0 | 151821 | 151821 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9883-25 | Procurement of Laminating Machine for use in the Provision of Safety & Health Signages, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-21 | N/A | 2025-12-26 | N/A | 2025-12-22 | 2025-12-22 | GOP | Ban Bee Comm'l Co., Inc. | 4500 | 4500 | 0 | 4200 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9885-25 | Procurement of Laminating Film for the Provision of Safety and Health Signages, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-26 |  | 2025-12-01 | N/A | 2025-12-05 | 2025-12-17 | GOP | Ban Bee Comm'l Co., Inc. | 3682 | 3682 | 0 | 3540 | 3540 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9889-25 | Supply & Delivery of Various Office Supplies for the 4th Qtr. 2025 | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | N/A |  |  | N/A | 2025-12-22 |  | 2025-12-26 | N/A | 2025-12-29 | - | GOP | Mostaco Marketing | 0 | 0 | 0 | 297569 | 297569 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 4
NH-9899-25 | PROCUREMENT OF ALTERNATOR PULLY #27415-300100 FOR TOYOTA HILUX YEAR MODEL 2020 WITH PLATE NO. SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-24 | GOP | H & T Auto Supply | 5500 | 5500 | 0 | 5205.36 | 5205.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9901-25 | Procurement of Hospital Bed, Stethoscope, Glucose Meter, Oxygen Tank, 5lbs, Trauma Bag & Infrared Thermometer, for NCRN Clinic Use. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-11 | N/A | 2025-12-23 | 2026-01-06 | GOP | BND Pharma and Medical Supplies Distribution Corp. | 45000 | 45000 | 0 | 42000 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9902-25 | Supply & Delivery of Chairs, Tables and Cabinets, for use at Various NCRN Offices | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-09 | 09-29-25 | 2025-12-15 | N/A | 2025-12-16 | 2025-12-22 | GOP | Progresss Home & Office Furnishing | 136000 | 136000 | 0 | 131795 | 131795 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9907-25 | Procurement of 2-units Desktop Computer, for use of Newly Hired Personnel. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 |  | 2025-12-15 | N/A | 2025-12-15 | 2026-01-05 | GOP | Masangkay Computer Center | 98000 | 98000 | 0 | 97776 | 97776 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9912-25 | Procurement of Catering Service for 2025 Year End Thanksgiving Celebration | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | N/A | 2025-12-17 | N/A | 2025-12-18 | 2025-12-18 | GOP | Matt's Catering | 150000 | 150000 | 0 | 150000 | 150000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9916-25 | Procurement of 37-pcs. Acrylic Wall Frame, for the provision of Emergency Exit Layout Plan, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-11 |  | 2025-12-22 | N/A | 2025-12-26 | - | GOP | Jarin Art Sign & Gen. Mdse | 21000 | 21000 | 0 | 20350 | 20350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9917-25 | Supply, Delivery & Installation of Hazardous Waste Storage Facility & Materials Recovery Facility, for IMS Compliance | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-09-16 | N/A | N/A | 2025-10-01 | 2025-10-29 | N/A | 2025-11-05 |  | 2025-11-20 | N/A | 2026-01-14 | - | GOP | Jameda Int'l. Enterprises | 500000 | 500000 | 0 | 498400 | 498400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9917-25 | Procurement of Service for Comprehensive General Pest & Termite Control Service for Various NCRN Office | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-12-14 | N/A | N/A | 2025-12-19 | 2025-12-23 | N/A | 2025-12-23 |  | 2025-12-26 | N/A | 2025-12-29 | - | GOP | JTO PEST CONTROL SERVICES | 241529 | 241529 | 0 | 86950.44 | 86950.44 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9950-25 | PROCUREMENT OF TWO (2) UNITS OF 2.5" SOLID STATE DRIVE FOR DESKTOP COMPUTER AT RMD FINANCE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 | GOP | PC Express | 6000 | 6000 | 0 | 5180 | 5180 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9962-25 | Procurement of three (3) units Date & Time Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 |  | 26-15-25 | N/A | 2025-12-29 | - | GOP | Triple Eight Business Equipment Corp. | 58883 | 58883 | 0 | 57000 | 57000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9963-25 | Supply & Delivery and Installation of 10-foot Container Van for Chemical Storage | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 |  | 2025-12-29 | N/A | 2025-12-29 | 2025-01-12 | GOP | Gold Mantis Builders & Trade Co. Inc. | 117000 | 117000 | 0 | 112000 | 112000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | ACETYLENE TANK REFILL FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-22 | GOP | - | 12300 | 12300 | 0 | 12300 | 12300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9593-25 | BRAKEPAD AND BRAKE SHOE FOR HYUNDAI STAREX WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | GOP | - | 11000 | 11000 | 0 | 11500 | 11500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9567-25 | DIGITAL WEIGHING SCALE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | GOP | Mart and Drug Convience Store Inc. | 3000 | 3000 | 0 | 1500 | 1500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9623-25 | EXHAUST PIPE EXTENSION FOR ISUZU DROPSIDE BOOM TRUCK YEAR MODEL 2022 WITH PLATE NO. D2S-061 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP | - | 6800 | 6800 | 0 | 6800 | 6800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9928-25 | PROCUREMENT OF BATTERIES FOR THE FIRE ALARM SYSTEM AT RS2-CORREGIDOR ISLAND | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GOP | - | 4000 | 4000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| PROCUREMENT OF BATTERIES FOR TOYOTA HILUX (2020) WITH PLATE NO. NBH-6409, HYUNDAI STAREX WITH PLATE NO. NOW-832 TOYOTA HILUX WITH PLATE NO. SND-2744 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GOP | - | 35000 | 35000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| PROCUREMENT OF ONE (1) PC DATER AND ONE (1) PC STAMPING MACHINE TO BE USED FOR OVERTIME REQUEST/ACCOMPLISHMENTS AND OTHER DOCUMENTS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | GOP | Ban Bee Comm'l Co., Inc. | 2900 | 2900 | 0 | 2230 | 2230 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | OXYGEN AND ACETYLENE REGULATOR SET | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-20 | GOP | - | 12300 | 12300 | 0 | 12300 | 12300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9615-25 | PREVENTIVE MAINTENANCE 80,000 KILOMETER CHECK UP FOR HONDA CRV MODEL 2020 WITH PLATE NO. NGJ-9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | GOP | - | 45000 | 45000 | 0 | 33983.71 | 33983.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF CUSHION | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-26 | GOP | - | 2000 | 2000 | 0 | 560 | 560 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9606-25 | PROCUREMENT OF DUAL CAPACITOR FOR ACU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-30 | GOP | - | 1000 | 1000 | 0 | 950 | 950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PROCUREMENT OF FIVE (5) LITERS OF COOLANT FOR MOTOR VEHICLES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | - | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
NH-9882-25 | PROCUREMENT OF GARDEN HOSE REEL 1/2" COMPLETE WITH SPRAY GUN NOZZEL 20MTRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-22 | N/A | N/A | N/A | 2025-12-23 | GOP | - | 4000 | 4000 | 0 | 3217.63 | 3217.63 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PROCUREMENT OF GARDEN HOSE, HOSE NOZZLE AND BRASE HOSE TO BE USED FOR CLEANING BY PMO NCR NORTH JANITORIAL PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | - | 3000 | 3000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| PROCUREMENT OF ONE (1) PC OF 2 IN 1 MAGNETIC INTERCHANGEABLE SCREWDRIVER 2 INCHES, TWO (2) PCS OF MAGNETIC SCREW DRIVER 6 INCHES NEGATIVE AND TWO (2) PCS OF MAGNETIC SCREWDRIVER 6 INCHES POSITIVE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | N/A | 1000 | 1000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| PROCUREMENT OF ONE (1) UNIT OF POWER SUPPLY UNIT (PSU) TO BE USED BY TSD - PLAU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-07 | GOP | PC Express | 5000 | 5000 | 0 | 2900 | 2900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PROCUREMENT OF ONE HUNDRED (100) PACKS OF RENNAISANCE LAID PAPER 100GSM | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-11 | N/A | N/A | N/A | N/A | GOP | - | 10000 | 10000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
NH-9610-25 | PROCUREMENT OF ONE SET OF OIL SEAL REAR AXEL FOR TOYOTA INNOVA YEAR MODEL 2008 WITH TEMP. PLATE NO. 030806 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 |  | 2025-07-07 | N/A | 2025-07-07 | 2025-07-07 | GOP | Grandmah;e Corporation | 1400 | 1400 | 0 | 1400 | 1400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9832-25 | PROCUREMENT OF RADIATOR ASSEMBLY OF HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-10-07 | GOP | - | 10500 | 10500 | 0 | 9937.5 | 9937.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF SERVICE FOR UPHOLSTERY OF VARIOUS FURNITURES AT PMO NCR NORTH | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP |  | 50000 | 50000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| PROCUREMENT OF SERVICES FOR THE CONDUCT OF MANDATORY DRUG TEST FOR PMO NCR NORTH PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 | 2025-12-01 | 2025-09-09 | 2025-09-10 | 2025-11-12 | 2025-11-12 | GOP | Medical Benefit Clearing House Inc. | 107000 | 107000 | 0 | 40200 | 40200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9453-25 | SUPPLY AND DELIVERY OF MOTORCYCLE GEAR ACCESSORIES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-06 | GOP | Teens Trendy Shoppe | 14000 | 14000 | 0 | 5645 | 5645 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9710-25 | PROCUREMENT OF T8 18W LED 6500 1800LM 170 DAYLIGHT TO BE USED TO REPLACE BUS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2025-08-19 | N/A | GOP | Kesco Industrial Sales Corporation | 1000 | 1000 | 0 | 1200 | 1200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF THIRTY (30) PCS OF A4 SIZE FRAME, FIFTY (50) PCS OF 8.5 X 13 FRAME TO BE USED FOR CERTIFICATION BY ADMIN - PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-08 | N/A | N/A | N/A | N/A | GOP | - | 12000 | 12000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF THREE (3) PCS NAME STAMP AND ONE (1) PC DATER FOR COA PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 | GOP | Ban Bee Comm'l Co., Inc. | 3150 | 3150 | 0 | 2580 | 2580 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9681-25 | PROCUREMENT OF THREE (3) TANKS OF MAPP GAS AND ONE (1) CYLINDER OF R22 REFRIGERANT | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-29 | GOP | - | 12600 | 12600 | 0 | 11000 | 11000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9684-25 | PROCUREMENT OF VARIOUS ACCESSORIES FOR PRESSURE WASHER TO BE USED FOR CLEANING THE MOTOR VEHICLE SERVICES AT PMO NCR NORTH | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-10-10 | GOP | - | 5250 | 5250 | 0 | 4821.43 | 4821.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF VARIOUS MATERIALS FOR 2025 YEAR-END THANKSGIVING CELEBRATION | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-15 | GOP | - | 15000 | 15000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF VARIOUS MATERIALS FOR THE TREE PLANTING AND COASTAL CLEAN-UP ACTIVITY | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-01 | GOP | Kesco Industrial Sales Corporation | 5000 | 5000 | 0 | 4444 | 4444 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9933-25 | PROCUREMENT OF VARIOUS STAMP TO BE USED BY RECORDS UNIT | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-28 | N/A | N/A | N/A | 2025-12-26 | GOP | Jarin Art Sign & Gen. Mdse | 3450 | 3450 | 0 | 3450 | 3450 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PURCHASE OF OXYGEN REFILL FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-09-04 | GOP | - | 2000 | 2000 | 0 | 1651.79 | 1651.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PURCHASE OF PAINT AND VARIOUS MATERIALS FOR REPAINTING WORKS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-07 | GOP | - | 12000 | 12000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9753-25 | PURCHASE OF SEALANTS, WATERPROOFING AND VARIOUS CONSTRUCTION MATERIALS FOR THE EMERGENCY REPAIR OF DAMAGED ROOFING | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-19 | GOP | - | 15000 | 15000 | 0 | 14191.7 | 14191.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9919-25 | PURCHASE OF STAINLESS STEEL DOORKNOBS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-17 | GOP | - | 3500 | 3500 | 0 | 2516 | 2516 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9767-25 | PURCHASE OF TWIN HOSE (OXYGEN-ACETYLENE) FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-24 | GOP | - | 4000 | 4000 | 0 | 2480.36 | 2480.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9565-25 | REPLACEMENT OF FAN RELAY AND SIDE MIRROR FOR HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-04-30 | GOP | - | 14350 | 14350 | 0 | 14350 | 14350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9564-25 | REPLACEMENT OF OIL FILTER, AIR FILTER, FUEL FILTER, CABIN FILTER FOR HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-04-30 | GOP | - | 5750 | 5750 | 0 | 5750 | 5750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLY AND DELIVERY OF BATTERY FOR GENERATOR SET AT RS-2 CORREGIDOR ISLAND | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-05 | GOP | Batparts Supply Co., Inc. | 10000 | 10000 | 0 | 7130 | 7130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLY AND DELIVERY OF CLEANING MATERIALS TO BE USE FOR IMS COMPLIANCE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | - | 53105 | 53105 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| SUPPLY AND DELIVERY OF DUAL WAY WINDOW SPEAKER SYSTEM | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-15 | N/A | N/A | N/A | N/A | GOP | - | 10000 | 10000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
| SUPPLY AND DELIVERY OF LAMINATING MACHINE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-15 | N/A | N/A | N/A | N/A | GOP | - | 25000 | 25000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
1-lot | PURCHASE OF PAINT AND VARIOUS MATERIALS FOR REPAINTING WORKS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-07 | GOP |  | 12000 | 12000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9640-25 | SUPPLY AND DELIVERY OF POWER SUPPLY UNIT (PSU) SEMI MODULAR 80 PLUS BRONZE 650 WATTS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-03 | GOP | - | 4000 | 4000 | 0 | 2900 | 2900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Petty Cash
| SUPPLY AND DELIVERY OF PPA LETTERHEAD | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | - | 50000 | 50000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured |  |  |  | 7
| SUPPLY AND DELIVERY OF VARIOUS ENVIRONMENTAL SIGNAGES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-29 | N/A | N/A | N/A | N/A | GOP | - | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
NH-9959-25 | SUPPLY AND DELIVERY OF VARIOUS MATERIALS FOR THE PREVENTIVE MAINTENANCE OF ICT EQUIPMENTS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | GOP | - | 50000 | 50000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not procured
NH-9445-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9429-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-20 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9419-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9427-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-20 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | GOP |  | 600 | 600 | 0 | 350 | 350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9438-25 | Wheel Rubber and Bolt & Nut | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | GOP |  | 1740 | 1740 | 0 | 1553.57 | 1553.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9428-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9456-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9488-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9497-25 | Cross joint Innova & Center Bearing Assembly | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | GOP |  | 9500 | 9500 | 0 | 9500 | 9500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9464-25 | Injection Pump Calibration | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | GOP |  | 11050 | 11050 | 0 | 11050 | 11050 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire - SND 2280, SLG 382 and SAB 4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | GOP |  | 2200 | 2200 | 0 | 2187.49 | 2187.49 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair and maintenance of service vehicle (Hyundai Starex 2017 with Plate no NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | GOP |  |  |  | 0 | 17946.43 | 17946.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9587-25 | For vulcanizing flat tire Toyota Hlux Plate No SND-2280 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | GOP |  | 1200 | 1200 | 0 | 1071.43 | 1071.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH=9642-25 | For use of Toyota Grandia with Plate No SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | GOP |  | 1200 | 1200 | 0 | 1071.43 | 1071.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9576-25 | For vulcanizing flat tire Toyota Grandia Plat e No SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9614-25 | For vulcanizing flat tire Toyota Commuter Plate No. SND-2264 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Hilux SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 500 | 500 | 0 | 446.43 | 446.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9661-25 | Vulcanizing Flat Tire Hyundai Starex NOW 832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-07 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9721-25 | Break Cleaner For Toyota Innova Temp Plate 030806 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-30 | GOP |  | 600 | 600 | 0 | 562.5 | 562.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9701-25 | Auxillary Power Relay Fuse 95225-38050 120v 10/20 AMP | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-08 | GOP |  | 6000 | 6000 | 0 | 5357.14 | 5357.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire HONDA CRV NDJ 9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-08 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9889-25 | Alternator Pulley, Carbon Brush Holder Assy For Honda CRV NDJ 9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 | GOP |  | 5500 | 5500 | 0 | 4700 | 4700 | 0 | 5205.36 | [6 empty] | PETTY CASH
NH-9763-25 | Flasher Realy Assy For Hyundai Grand Starex with Plate No NOW 832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-24 | GOP |  | 3500 | 3500 | 0 | 3125 | 3125 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Toyota Grandia SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Hyundai Starex NOW-892 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | GOP |  | 1000 | 1000 | 0 | 835.71 | 835.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| For use service vehicle Hyundai Starex Plate No NBC 6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | GOP |  |  |  | 0 | 9375 | 9375 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9937-25 | Vulcanizing Flat Tire - Hyundai Starex Plate No NOW-832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-12 | GOP |  | 600 | 600 | 0 | 600 | 600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9899-25 | Head Light Bulb Hyudai Starex NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Replacement for Defective Battery - 3SMF N70 Engine Battery | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | GOP |  | 10000 | 10000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9437-25 | Repair and Maintenance of Phorocopier HP Copier Model E72630dn - 1 pc ADF Pick-up Assembly, 1 pc Laser Scanning Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | GOP |  | 15000 | 15000 | 0 | 12410.71 | 12410.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9439-25 | Repair and Maintenance of Various ACU NCR North - Copper Tube, Copper Elbow 2 pcs, Copper Coupling 2 pcs | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | GOP |  | 3620 | 3620 | 0 | 3232.14 | 3232.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9468-25 | Maintenance of sound system and ACU's board - Contact Cleaner Oil | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | GOP |  | 1000 | 1000 | 0 | 875 | 875 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9551-25 | Repair of ACU - Refrigerant, Access Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | GOP |  | 7500 | 7500 | 0 | 6696.43 | 6696.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9634-25 | Repair and replacement defective spare parts pressure washer. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | GOP |  | 1000 | 1000 | 0 | 892.86 | 892.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair of ACU - Dual Capacitor | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | GOP |  | 1000 | 1000 | 0 | 848.21 | 848.21 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repairing of ACU located at entrance lobby PPA NCR North - Pressure Switch & MAPP Gas | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 2767.86 | 2767.86 | 0 | 2767.86 | 2767.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair and maintenance of Comfort Room located at PWD and Men CR Lobby area - Bidet/Tank Lever/Lavatory/Faucet/Teflon | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 1392.86 | 1392.86 | 0 | 1392.86 | 1392.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PSU Semi Modular 80 plus Bronze 650 Watts | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | GOP |  | 3000 | 3000 | 0 | 2589.29 | 2589.29 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| One set Circuit Breaker 50AMP | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-29 | GOP |  | 4000 | 4000 | 0 | 3750 | 3750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Lock | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-21 | GOP |  | 2000 | 2000 | 0 | 1740 | 1740 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9857-25 | Unit Contractor Switch relay 40 amp - 3rd flr acu | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-29 | GOP |  | 2500 | 2500 | 0 | 2500 | 2500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9540-25 | Paper Cup and Wooden Spoon | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 1178.57 | 1178.57 | 0 | 1178.57 | 1178.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9583-25 | Zonrox, Powder Soap | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | GOP |  | 520 | 520 | 0 | 429.24 | 429.24 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9561-25 | 2-Way Angle Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | GOP |  | 500 | 500 | 0 | 280 | 280 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9619-25 | USB Microphone DCM 001U DC 4,5 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-30 | GOP |  | 2000 | 2000 | 0 | 1116.07 | 1116.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9776-25 | Plastic Trash Bag (Medium, XL) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-25 | GOP |  | 6000 | 6000 | 0 | 5000 | 5000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9792-25 | Repair of Customer Feedback Surevey Box | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-15 | GOP |  | 1000 | 1000 | 0 | 1000 | 1000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9788-25 | Glue Board | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 | GOP |  | 1250 | 1250 | 0 | 2000 | 2000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9794-25 | Green and Blue Plastic Celophane - National Maritime Weeek | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 | GOP |  | 780 | 780 | 0 | 780 | 780 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9960-25 | Nylon Rope | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-26 | GOP |  | 80 | 80 | 0 | 80 | 80 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9677-25 | Keybox Holder | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-07 | GOP |  | 3000 | 3000 | 0 | 2008.04 | 2008.04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH- | ISO Standards Manuals | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-06 | GOP |  | 1160 | 1160 | 0 | 1160 | 1160 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Three (3) pcs Certificate Frames | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-24 | GOP |  | 1000 | 1000 | 0 | 650 | 650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9436-25 | Reinassance Laid Paper 8 1/2x13 White 100gsm | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | GOP |  | 3250 | 3250 | 0 | 2678.57 | 2678.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9470-25 | Automatic numbering stamp for used of Cashiering Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | GOP |  | 2000 | 2000 | 0 | 1784.82 | 1784.82 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9528-25 | Automatic numbering stamp for used of Cashiering Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | GOP |  | 2000 | 2000 | 0 | 1867.86 | 1867.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Cash Box, Mouse Trap and Mouse Sticky Trap | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | GOP |  | 4000 | 4000 | 0 | 2433.04 | 2433.04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9481-25 | Three (3) pcs Rubber Stamp | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | GOP |  | 2250 | 2250 | 0 | 2250 | 2250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9529-25 | Rubber Stamp | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | GOP |  | 800 | 800 | 0 | 800 | 800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9529-25 | Two (2) pcs Certificate Holder | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | GOP |  | 300 | 300 | 0 | 260 | 260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9530-25 | Two (2) pcs Frames | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | GOP |  | 300 | 300 | 0 | 260 | 260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9548-25 | Corkboard | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | GOP |  | 2000 | 2000 | 0 | 1651.79 | 1651.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9590-25 | Pilot Hi-Techpoint 07 RT - Blue | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | GOP |  | 1000 | 1000 | 0 | 2057.14 | 2057.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9723-25 | Double Mounting Tape | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-06 | GOP |  | 4750 | 4750 | 0 | 4241.07 | 4241.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9649-25 | Dater and Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | GOP |  | 2900 | 2900 | 0 | 2303.57 | 2303.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9783-25 | Dater and Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | GOP |  | 2000 | 2000 | 0 | 1991.07 | 1991.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9726-25 | Vellum Board | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-12 | GOP |  | 3000 | 3000 | 0 | 660.71 | 660.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9643-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | GOP |  | 750 | 750 | 0 | 615.18 | 615.18 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | GOP |  | 100 | 100 | 0 | 100 | 100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9644-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | GOP |  | 2040 | 2040 | 0 | 1930.71 | 1930.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9648-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | GOP |  | 3745 | 3745 | 0 | 3544.38 | 3544.38 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9657-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | GOP |  | 878 | 878 | 0 | 830.96 | 830.96 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9658-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 380 | 380 | 0 | 359.64 | 359.64 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9662-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-02 | GOP |  | 116 | 116 | 0 | 116 | 116 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9690-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 390 | 390 | 0 | 369.11 | 369.11 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9671-25 | Oxygen | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-11 | GOP |  | 1000 | 1000 | 0 | 520.54 | 520.54 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9689-25 | Acetylene | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-11 | GOP |  | 2000 | 2000 | 0 | 1750.89 | 1750.89 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9696-25 | Oxygen | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 | GOP |  | 600 | 600 | 0 | 520.54 | 520.54 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9724-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-12 | GOP |  | 915 | 915 | 0 | 865.98 | 865.98 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9733-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-13 | GOP |  | 180 | 180 | 0 | 180 | 180 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9747-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-15 | GOP |  | 230 | 230 | 0 | 230 | 230 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9789-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 | GOP |  | 795 | 795 | 0 | 752.41 | 752.41 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9811-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-17 | GOP |  | 285 | 285 | 0 | 285 | 285 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9816-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1901-01-31 | GOP |  | 420 | 420 | 0 | 397.5 | 397.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9817-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-25 | GOP |  | 170 | 170 | 0 | 170 | 170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9822-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | GOP |  | 50 | 50 | 0 | 50 | 50 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9828-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-02 | GOP |  | 300 | 300 | 0 | 300 | 300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9835-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-13 | GOP |  | 997.5 | 997.5 | 0 | 944.06 | 944.06 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9682-25 | PROCUREMENT OF TWENTY-FIVE (25) PACKS OF FOLDER DIVIDER (A4),TWENTY-FIVE (25) PACKS OF FOLDER DIVER (LEGAL), ELEVEN (11) PACKS OF PLASTIC SLIDING FOLDER (CLEAR), ONE (1) REAM OF COLORED PAPER (ASSORTED COLOR) AND TWO (2) PACKS OF STICKER PAPER (GLOSSY) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-31 | GOP | - | 6000 | 6000 | 0 | 3580 | 3580 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
Total Allotted Budget of Procurement Activities | [18 empty] | 10139224.59
Total Contract Price of Procurement Activities Conducted | [18 empty] | 9026522.93
Total Savings(Total Alloted Budget - Total Contract Price | [18 empty] | 1112701.66
| Prepared by: |  |  |  | Reviewed by: | [9 empty] | Recommending Approval: | [10 empty] | Noted by: | [6 empty] | Recommending Approval: | Noted by:
| JEYMER M. SELOSA |  |  |  | MARISA T. ARIMADO | [9 empty] | FRANCIS ALDRICH A. RUBIO | [10 empty] | JENNELIZA D. REBONG | [6 empty] | FRANCIS ALDRICH A. RUBIO | JENNELIZA D. REBONG
| BAC , Support Staff |  |  |  | BAC Secretariat, Head | [9 empty] | BAC-NCRN Chairperson | [10 empty] | Port Manager / Head of Procuring Entity | [6 empty] | BAC-NCRN Chairperson | Port Manager / Head of Procuring Entity

## Jul - Dec (2)
ANNEX B
Philippine Ports Authority - Port Management Office of NCR North Procurement Monitoring Report as of July-December 2025
Code (PAP) PR No. | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds |  | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP) |  |  | PAYMENTS
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | P.O # | Contract Signing/P.O | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | SUPPLIER | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Accept
Completed Procurement Activities
NH-9927-25 | Procurement of 1-pc. Automotive Battery, 3SMF, 12V, for Genset located at NCRN Admin Bldg. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GOP |  | 9000 | 9000 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9951-25 | PROCUREMENT OF HANDSOAP DISPENSER AND TISSUE HOLDER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-22 | GOP | Ace Hardware Phils. Inc. | 13000 | 13000 | 0 | 7088.75 | 7088.75 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF ONE (1) PC KEYBOX HOLDER TO BE USED AT PMO NCR NORTH LOBBY | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-20 | N/A | N/A | N/A | 2025-09-02 | GOP | Ace Hardware Phils. Inc. | 3000 | 3000 | 0 | 2128.52 | 2128.52 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF ONE (1) UNIT OF UPS 650 VA, ONE (1) PC SURGER PROTECTOR AND FIVE (5) UNITS OF 4 PORT HUB TO BE USED BY COA PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | N/A | N/A | N/A | 2025-10-21 | GOP | PC Express / Ugreen | 9300 | 9300 | 0 | 9059 | 9059 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF CALLING CARD FOR USED OF THE PORT MANAGER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-12 | GOP | Pinagpala Printing Press | 3000 | 3000 | 0 | 1425 | 1425 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PROCUREMENT OF FIFTEEN (15) PCS OF CERTIFICATE FRAMES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | GOP | National Bookstore | 2000 | 2000 | 0 | 1950 | 1950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9945-25 | Procurement of Floor Matting to be used at PMO NCR North Lobby | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2025-12-31 | ON GOING | GOP | Ban Bee Comm'l Co., Inc. | 12000 | 12000 | 0 | 10194.9 | 10194.9 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF FOURTEEN (14) PCS OF CUSTOMIZED A3 FRAME FOR ORGANIZATIONAL CHART | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | N/A | N/A | N/A | 2025-08-02 | GOP |  | 14000 | 14000 | 0 | 13300 | 13300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9699-25 | PROCUREMENT OF ONE (1) PAIR OF SAFETY SHOES TO USED BY THE PORT MANAGER | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-31 | GOP |  | 3500 | 3500 | 0 | 1817.36 | 1817.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | Supply & Delivery of 2-units Radiator Assembly and 1-Water Pump Assembly for RS-2 15KVA Genset | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2025-12-29 | ON GOING | GOP | Zayne Medfical Supplies | 210000 | 210000 | 0 | 198056.32 | 198056.32 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9920-25 | Supply & Delivery of 4-pcs. Yokohama Tires, 265/665 R17, for T. Hi-Lux Mobile Patrol, NBH-6409, PPD | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-29 | N/A | 2025-12-29 | ON GOING | GOP | Grandmah;e Corporation | 62000 | 62000 | 0 | 62000 | 62000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9742-25 | SUPPLY AND DELIVERY OF 3 UNIT FIRE HOSE CABINET WITH 100-FT FIRE HOSE DOUBLE JACKET | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26-15-25 | 2025-12-29 | N/A | 2025-12-29 | ON GOING | GOP | Tigronyx Fire Safety Inc. | 52500 | 52500 | 0 | 31470 | 31470 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF ONE (1) UNIT OF CALCULATOR 14 DIGITS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-29 | GOP | Ban Bee Comm'l Co., Inc. | 1000 | 1000 | 0 | 850 | 850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9132-25 | Procurement of Scanner, Printers and Dot Matrix Printers, for Various NCRN Office Use | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 |  | 2025-12-11 | N/A | 2015-12-13 | 2026-01-06 | GOP | URQUAN INC. | 145000 | 145000 | 0 | 134210 | 134210 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9136-25 | Supply & Delivery of 1-pc. 3SMF N70 Engine Battery, for use at T. Hi-Lux, Plate No. SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-18 | N/A | 2025-12-18 | 2025-01-05 | GOP | MarkPower Enterprises | 8000 | 8000 | 0 | 6800 | 6800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9457-25 | Procurement of LED Warning Light 10-30 Volts | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 |  | 2025-06-19 | N/A | 2025-06-19 | 2025-07-01 | GOP | Grandmah;e Corporation | 11520 | 11520 | 0 | 10500 | 10500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9492-25 | Supply and Delivery of Cabinets | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-04-22 | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-20 |  | 2025-07-07 | N/A | 2025-07-09 | 2025-07-19 | GOP | GOP | 200000 | 200000 | 0 | 89600 | 89600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9569-25 | Supply and Delivery of Batteries for Various Motor Vehicles | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 |  | 2025-06-05 | N/A | 2025-06-19 | 2025-06-20 | GOP | Batparts Supply Co., Inc. | 86000 | 86000 | 0 | 52021 | 52021 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9570-25 | Supply and Delivery of Tires for Toyota Commuter (2024) with Plate no. SND-2264, Toyta Hi-Lux (2024) with Plate no. SND-2280 and Toyota Grandia (2017) with Plate No. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-30 | N/A | 2025-06-20 |  | 2025-06-25 | N/A | 2025-06-29 | 2025-07-01 | GOP | Tire Asia Group Inc. | 125000 | 125000 | 0 | 83325 | 83325 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9579-25 | Supply and Delivery of Various Office Supplies for 2nd Quarter of CY 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | 2025-05-27 | N/A | N/A | 2025-06-09 |  | 2025-07-09 | N/A | 2025-07-31 | 2025-08-01 | GOP | Mostaco Mktg. | 376295.8 | 376295.8 | 0 | 343608 | 343608 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2
NH-9580-25 | Supply and Delivery of Marine LogBook | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 |  | 2025-06-16 | N/A | 2025-07-04 | 2025-07-07 | GOP | Ban Bee Comm'l Co., Inc. | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 5
NH-9596-25 | Supply and Delivery of 3SMF Battery for Toyota Hilux Year Model 2013 with Plate No. POJ-331 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 |  | 2025-06-19 | N/A | 2025-06-19 | 2025-07-01 | GOP | 10000 | 10000 | 10000 | 0 | 7130 | 7130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9611-25 | Supply and Delivery of Tubeless Tires 215/70 R16C for Hyundai Starex Year Model 2018 with Plate No. NBC-6114 including Tire Mounting and Tire Balancing | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 |  | 2025-06-25 | N/A | 2025-06-28 | 2025-07-01 | GOP | Tire Asia Group Inc. | 54000 | 54000 | 0 | 43645 | 43645 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9617-25 | Procurement of 1-unit All In One Desktop Computer, for use of COA | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 09-17-25 | 2025-06-27 | N/A | 2025-07-30 | 2025-08-14 | GOP | Masangkay Computer Center | 50000 | 50000 | 0 | 49998 | 49998 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9624-25 | PROCUREMENT OF SERVICE FOR THE INSPECTION AND REPAIR OF ONE (1) UNIT EATON FIRE ALARM SYSTEM AT THE VTMS CONTROL CENTER BUILDING, MICT, TONDO MANILA | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-07-03 | N/A | N/A | 2025-07-18 | 2025-07-30 | 2025-07-30 | 2025-08-13 | 12-03-25 | 2025-08-22 | N/A | 2025-08-24 | 2025-12-09 | GOP | Iptek Comm. Co. Ltd. | 80000 | 80000 | 0 | 75000 | 75000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9647-25 | Supply and Delivery of Submersible Water Pump | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 |  | 2025-08-04 | N/A | 2025-08-11 | 2025-08-14 | GOP | Sonitram Mdsg Corp. | 15000 | 15000 | 0 | 11800 | 11800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9660-25 | Supply, Delivery and Installation of 1HP Window Type Aircondition Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | 2025-12-14 | N/A | N/A | 2025-12-19 | 2025-12-23 | N/A | 2025-12-22 |  | 2025-12-29 | N/A | 2025-12-29 | ON GOING | GOP | O Plus | 99000 | 99000 | 0 | 92396 | 92396 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9676-25 | Supply & Delivery of Phil., Flag, DOTr & PPA Flag, for use at NCRN Offices | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | 11-03-25 | 2025-07-31 | N/A | 2025-10-10 | 2025-10-10 | GOP | Atlas Super Flags | 47400 | 47400 | 0 | 35400 | 35400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9678-25 | Procurement of 450-pcs. Sacks, 50kls capacity, for use at NCRN Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | 09-17-25 | 2025-07-31 | N/A | 2025-08-01 | 2025-08-14 | GOP | AE Samonte Mdse. | 11250 | 11250 | 0 | 8325 | 8325 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9679-25 | Procurement of Whiteboards | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 |  | 2025-07-31 | N/A | 2025-08-07 | 2025-08-14 | GOP | AE Samonte Mdse. | 34400 | 34400 | 0 | 33650 | 33650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9680-25 | Supply & Dedlivery of Assorted Trashbins, for IMS Compliance | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-08-12 | N/A | N/A | 2025-09-08 | 2025-09-08 | N/A | 2025-09-29 | 12-03-25 | 2025-10-08 | N/A | 2025-11-17 | 2025-11-19 | GOP | Abeltrade Ent. Corp. | 214000 | 214000 | 0 | 140885 | 140885 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9700-25 | Procurement of Various LED Lights for the Buidings & Office of NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 170000 | 170000 | 0 | 160320 | 160320 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9702-25 | Procurement of Metal Works & Various Construction Equipment for In-House Routinary R&M of Buildings at NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 86450.1 | 86450.1 | 0 | 86430 | 86430 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9703-25 | Procurement of Various Electrical Materials for Buildings & Offices at NCRN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | 10-02-25 | 2025-09-09 | N/A | 2025-09-30 | 2025-09-30 | GOP | Sonitram Mdsg Corp. | 85344 | 85344 | 0 | 85312 | 85312 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9714-25 | Procurement of Service for Mobilization of Flr Mounted ACU, from Annex Bldg. to VTMS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-29 | 12-05-25 | 2025-10-13 | N/A | 2025-10-15 | 2025-12-24 | GOP | AVF Airconditioning Center | 26000 | 26000 | 0 | 24300 | 24300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9715-25 | Procurement of Service for Leak Repair & Reprocessing of ACU, TMO Vitas | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 | 12-05-25 | 09-30-25 | N/A | 2025-10-15 | 2025-11-24 | GOP | AVF Airconditioning Center | 14500 | 14500 | 0 | 13800 | 13800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9718-25 | Procurement of Furnitures, for use at the Office of the PM Waiting Area | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-21 |  | 2025-11-12 | N/A | 2025-11-12 | 2025-12-05 | GOP | Casamia Furniture Center, Inc. | 75000 | 75000 | 0 | 73465 | 73465 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9738-25 | Supply and Delivery of Various Safety and Health Signages | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 |  | 2025-10-14 | N/A | 2025-10-14 | 2025-10-28 | GOP | Jarin Art Sign & Gen. Mdse | 15000 | 15000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9739-25 | Supply & Delivery of Various Personal Protective Equipment (PPE) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 09-17-25 |  | 2025-11-13 | N/A | 2025-10-22 | 2025-12-22 | GOP | Hi-Safety Industrial Supplies Inc. | 75000 | 75000 | 0 | 35781.24 | 35781.24 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9740-25 | Supply & Delivery of Fireman Suit Cabinet, for IMS & BFP Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-18 | 12-03-25 | 2025-10-23 | N/A | 2025-10-27 | 2025-10-29 | GOP | Realsan Enterprises | 5000 | 50000 | 0 | 46000 | 46000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9741-25 | Supply & Delivery of Bokashi Compost Bins, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11-26-25 |  | N/A | N/A | 1941-01-24 | 1936-12-16 | GOP | Jarin Art Sign & Gen. Mdse | 15000 | 15000 | 0 | 13500 | 13500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9743-25 | Supply & Delivery of ABC and HCFC Fire Extinguisher | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-09-19 | N/A | N/A | 2025-10-29 | N/A | N/A | 2025-11-04 |  | N/A | N/A | 2025-12-05 | 2025-12-22 | GOP | ES Castro Trading | 295000 | 295000 | 0 | 72000 | 72000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9744-25 | Supply & Delivery of Various Oil Spill Recovery Materials, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-29 | 12-03-25 | 2025-10-14 | N/A | 2025-10-28 | 2025-10-28 | GOP | 30000 | 48100 | 48100 | 0 | 48100 | 48100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9775-25 | Supply, Delivery & Services of 600-Containers of Purified Drinking Water for twelve (12) months (Nov. 2025 to Oct. 2026) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-13 | N/A | N/A | 2025-10-24 | 2025-10-29 | 2025-10-29 | 2025-10-29 | N/A | 2025-10-30 | 2025-10-30 | ON GOING | ON GOING | GOP | Maris Pure Corp. | 314400 | 314400 | 0 | 314400 | 314000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9784-25 | Supply & Delivery of Various Office Supplies for the 3rd Qtr. 2025 | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | 2025-10-02 | 2025-10-02 | 2025-10-02 | N/A | N/A | 2025-10-02 | 11-07-25 | 2025-10-08 | N/A | 2025-10-16 | 2025-10-28 | GOP | Mostaco Mktg. | 310748.25 | 310748.25 | 0 | 308000 | 308000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 3
NH-9810-25 | Supply & Delivery of Janitorial Supplies for the 4th Qtr. 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-25 | 11-07-25 | 2025-10-03 | N/A | 2025-10-06 | 2025-10-28 | GOP | Kenleen Intl. Distribution, Inc. | 85227 | 85227 | 0 | 78082 | 78082 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9812-25 | Supply and Dellivery of Digital Blood Pressure Monitor, for use at Various NCRN Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-01 | 11-07-25 | 2025-10-20 | N/A | 2025-10-22 | 2025-10-28 | GOP | Aspire Appliance Marketing | 23000 | 23000 | 0 | 20216 | 20216 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9818-25 | PROCUREMENT OF ALTERNATOR ASSEMBLY FOR MITSUBISHI ADVENTURE YEAR MODEL 2013 WITH PLATE NO. SLG-382 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-11 | GOP | Richland Autosupply | 10000 | 10000 | 0 | 9800 | 9800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9839-25 | Maintenance of VTMS Radar Station 1 Facility at MICT, Tondo, Manila (MFP-NCN-04-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | 2025-12-01 | 2025-12-01 | 2025-12-09 | ON GOING | ON GOING | GOP | Big J Steel Construction Corp. | 983160 | 983160 | 0 | 963496.8 | 963496.8 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9840-25 | Maintenance of PMO NCR North Port Police Bldg., North Harbor, Tondo, Manila (MFP-NCN-02-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | ON GOING | ON GOING | GOP | Big J Steel Construction Corp. | 894950 | 894950 | 0 | 870202.5 | 870202.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9841-25 | Maintenance of PMO NCR North Annex Bldg. and Main Entrance Gate at North Harbor, Tondo, Manila (MFP-NCN-03-2025) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | ON GOING | ON GOING | GOP | Big J Steel Construction Corp. | 997102 | 997102 | 0 | 969482.27 | 969482.27 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9842-25 | Maintenance of PMO NCR North Admin. Bldg. Including Access Bridgeway at North Harbor, Tondo, Manila (COP-MFP-NCN-01-25) | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-10-29 | N/A | N/A | 2025-11-03 | 2025-11-06 | N/A | 2025-11-24 | N/A | 2025-12-01 | 2025-12-09 | ON GOING | ON GOING | GOP | Big J Steel Construction Corp. | 996638 | 996638 | 0 | 976997.98 | 976997.98 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9843-25 | Supply & Delivery of 10-bxs Toner Cartridge W1002YC for HP Photocopier Model E2630DN | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-21 |  | N/A | N/A | 2025-12-22 | 2026-01-05 | GOP | Data Images Pluls Automation Phils, Inc. | 80000 | 80000 | 0 | 66000 | 66000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9843-25 | Procurement of Degreaser to be used by Admin-GSU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12-19-25 |  | N/A | N/A | 2025-12-19 | 2026-01-05 | GOP | Kenleen Intl. Distribution Inc. | 8000 | 8000 | 0 | 4960 | 4960 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9859-25 | PROCUREMENT OF BRAKE SHOE, BRAKE MASTER ASSEMBLY AND BRAKE PAD FOR TOYOTA GRANDIA YEAR MODEL: 2017 WITH PLATE NO. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-05 | GOP | EDCM Auto Supply | 14500 | 14500 | 0 | 13775 | 13775 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9860-25 | Procurement of Power Steering Pump Assembly, for Hyundai Grand Starex, Model 2018, Plate no. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-08 | N/A | 2025-12-18 | 2025-01-05 | GOP | MarkPower Enterprises | 17000 | 17000 | 0 | 16800 | 16800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9862-25 | Supply & Delivery of Various Medical Supplies for Second Semester 2025 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-11 | N/A | 2025-12-23 | 2026-01-06 | GOP | BND Pharma and Medical Supplies Distribution Corp. | 37000 | 37000 | 0 | 28559.7 | 28559.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9867-25 | Procurement of Service for Refill and Reconditioning of Fire Extinguishers | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-11-05 | N/A | N/A | 2025-11-12 | N/A | N/A | 2025-11-24 |  | 2025-12-01 | N/A | 2025-12-16 | 2025-12-22 | GOP | ES Castro Trading | 55250 | 55250 | 0 | 28500 | 28500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9868-25 | PROCUREMENT OF ONE (1) PC DIFFUSER OIL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-30 | GOP | Scentsmith Perfumery Inc. | 1000 | 1000 | 0 | 998 | 998 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9873-25 | TIRE ALIGNMENT AND CAMBER CORRECTION OF TOYOTA GRANDIA WITH PLATE NO. SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-07 | GOP | Nes Tire Supply | 4000 | 4000 | 0 | 1200 | 1200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9879-25 | Procurement of Various Construction Materials, for Plumbing & Masonry Works for In-House Routinary R&M of Buildings & Office | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-21 |  | 2025-11-28 | N/A | 2025-12-16 | 2025-12-16 | GOP | Boston Builder's Center | 156159.65 | 156159.65 | 0 | 151821 | 151821 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9883-25 | Procurement of Laminating Machine for use in the Provision of Safety & Health Signages, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-21 | N/A | 2025-12-26 | N/A | 2025-12-22 | 2025-12-22 | GOP | Ban Bee Comm'l Co., Inc. | 4500 | 4500 | 0 | 4200 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9885-25 | Procurement of Laminating Film for the Provision of Safety and Health Signages, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-26 |  | 2025-12-01 | N/A | 2025-12-05 | 2025-12-17 | GOP | Ban Bee Comm'l Co., Inc. | 3682 | 3682 | 0 | 3540 | 3540 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9889-25 | Supply & Delivery of Various Office Supplies for the 4th Qtr. 2025 | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | N/A | 2025-12-19 | 2025-12-22 | N/A | 2025-12-22 |  | 2025-12-26 | N/A | 2025-12-29 | 2025-12-31 | GOP | Mostaco Marketing | 385326.8 | 385326.8 | 0 | 297569 | 297569 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 4
NH-9899-25 | PROCUREMENT OF ALTERNATOR PULLY #27415-300100 FOR TOYOTA HILUX YEAR MODEL 2020 WITH PLATE NO. SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-24 | GOP | H & T Auto Supply | 5500 | 5500 | 0 | 5205.36 | 5205.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9901-25 | Procurement of Hospital Bed, Stethoscope, Glucose Meter, Oxygen Tank, 5lbs, Trauma Bag & Infrared Thermometer, for NCRN Clinic Use. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 |  | 2025-12-11 | N/A | 2025-12-23 | 2026-01-06 | GOP | BND Pharma and Medical Supplies Distribution Corp. | 45000 | 45000 | 0 | 42000 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9902-25 | Supply & Delivery of Chairs, Tables and Cabinets, for use at Various NCRN Offices | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-09 | 09-29-25 | 2025-12-15 | N/A | 2025-12-16 | 2025-12-22 | GOP | Progresss Home & Office Furnishing | 136000 | 136000 | 0 | 131795 | 131795 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9907-25 | Procurement of 2-units Desktop Computer, for use of Newly Hired Personnel. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-01 |  | 2025-12-15 | N/A | 2025-12-15 | 2026-01-05 | GOP | Masangkay Computer Center | 98000 | 98000 | 0 | 97776 | 97776 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9912-25 | Procurement of Catering Service for 2025 Year End Thanksgiving Celebration | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-17 | N/A | 2025-12-17 | N/A | 2025-12-18 | 2025-12-18 | GOP | Matt's Catering | 150000 | 150000 | 0 | 150000 | 150000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9916-25 | Procurement of 37-pcs. Acrylic Wall Frame, for the provision of Emergency Exit Layout Plan, for IMS Compliance | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-11 |  | 2025-12-22 | N/A | 2025-12-26 | ON GOING | GOP | Jarin Art Sign & Gen. Mdse | 21000 | 21000 | 0 | 20350 | 20350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9917-25 | Supply, Delivery & Installation of Hazardous Waste Storage Facility & Materials Recovery Facility, for IMS Compliance | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-09-16 | N/A | N/A | 2025-10-01 | 2025-10-29 | N/A | 2025-11-05 |  | 2025-11-20 | N/A | 2026-01-14 | ON GOING | GOP | Jameda Int'l. Enterprises | 500000 | 500000 | 0 | 498400 | 498400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9917-25 | Procurement of Service for Comprehensive General Pest & Termite Control Service for Various NCRN Office | PMO-NCR North | Sec. 34 Small Value Procurement | N/A | 2025-12-14 | N/A | N/A | 2025-12-19 | 2025-12-23 | N/A | 2025-12-23 |  | 2025-12-26 | N/A | 2025-12-29 | ON GOING | GOP | JTO PEST CONTROL SERVICES | 241529 | 241529 | 0 | 86950.44 | 86950.44 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9950-25 | PROCUREMENT OF TWO (2) UNITS OF 2.5" SOLID STATE DRIVE FOR DESKTOP COMPUTER AT RMD FINANCE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 | GOP | PC Express | 6000 | 6000 | 0 | 5180 | 5180 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9962-25 | Procurement of three (3) units Date & Time Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 |  | 26-15-25 | N/A | 2025-12-29 | ON GOING | GOP | Triple Eight Business Equipment Corp. | 58883 | 58883 | 0 | 57000 | 57000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9963-25 | Supply & Delivery and Installation of 10-foot Container Van for Chemical Storage | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-23 |  | 2025-12-29 | N/A | 2025-12-29 | 2025-01-12 | GOP | Gold Mantis Builders & Trade Co. Inc. | 117000 | 117000 | 0 | 112000 | 112000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ACETYLENE TANK REFILL FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 | GOP | - | 2000 | 2000 | 0 | 1850 | 1850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9593-25 | BRAKEPAD AND BRAKE SHOE FOR HYUNDAI STAREX WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | GOP | - | 115000 | 11500 | 0 | 11500 | 11500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9567-25 | DIGITAL WEIGHING SCALE | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | GOP | Mart and Drug Convience Store Inc. | 3000 | 3000 | 0 | 1500 | 1500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9623-25 | EXHAUST PIPE EXTENSION FOR ISUZU DROPSIDE BOOM TRUCK YEAR MODEL 2022 WITH PLATE NO. D2S-061 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP | - | 6800 | 6800 | 0 | 6800 | 6800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PROCUREMENT OF ONE (1) PC DATER AND ONE (1) PC STAMPING MACHINE TO BE USED FOR OVERTIME REQUEST/ACCOMPLISHMENTS AND OTHER DOCUMENTS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-28 | GOP | Ban Bee Comm'l Co., Inc. | 2900 | 2900 | 0 | 2230 | 2230 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | OXYGEN AND ACETYLENE REGULATOR SET | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-20 | GOP | - | 12300 | 12300 | 0 | 12300 | 12300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9615-25 | PREVENTIVE MAINTENANCE 80,000 KILOMETER CHECK UP FOR HONDA CRV MODEL 2020 WITH PLATE NO. NGJ-9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | GOP | - | 45000 | 45000 | 0 | 33983.71 | 33983.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF CUSHION | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-26 | GOP | - | 2000 | 2000 | 0 | 560 | 560 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9606-25 | PROCUREMENT OF DUAL CAPACITOR FOR ACU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-30 | GOP | - | 1000 | 1000 | 0 | 950 | 950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9882-25 | PROCUREMENT OF GARDEN HOSE REEL 1/2" COMPLETE WITH SPRAY GUN NOZZEL 20MTRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-22 | N/A | N/A | N/A | 2025-12-23 | GOP | - | 4000 | 4000 | 0 | 3217.63 | 3217.63 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PROCUREMENT OF ONE (1) UNIT OF POWER SUPPLY UNIT (PSU) TO BE USED BY TSD - PLAU | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-07 | GOP | PC Express | 5000 | 5000 | 0 | 2900 | 2900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9610-25 | PROCUREMENT OF ONE SET OF OIL SEAL REAR AXEL FOR TOYOTA INNOVA YEAR MODEL 2008 WITH TEMP. PLATE NO. 030806 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 |  | 2025-07-07 | N/A | 2025-07-07 | 2025-07-07 | GOP | Grandmah;e Corporation | 1400 | 1400 | 0 | 1400 | 1400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9832-25 | PROCUREMENT OF RADIATOR ASSEMBLY OF HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-10-07 | GOP | - | 10500 | 10500 | 0 | 9937.5 | 9937.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF SERVICES FOR THE CONDUCT OF MANDATORY DRUG TEST FOR PMO NCR NORTH PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 | 2025-12-01 | 2025-09-09 | 2025-09-10 | 2025-11-12 | 2025-11-12 | GOP | Medical Benefit Clearing House Inc. | 107000 | 107000 | 0 | 40200 | 40200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9453-25 | SUPPLY AND DELIVERY OF MOTORCYCLE GEAR ACCESSORIES | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-06 | GOP | Teens Trendy Shoppe | 14000 | 14000 | 0 | 5645 | 5645 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9710-25 | PROCUREMENT OF T8 18W LED 6500 1800LM 170 DAYLIGHT TO BE USED TO REPLACE BUS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-19 | GOP | Kesco Industrial Sales Corporation | 1200 | 1200 | 0 | 1200 | 1200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF THREE (3) PCS NAME STAMP AND ONE (1) PC DATER FOR COA PERSONNEL | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 | GOP | Ban Bee Comm'l Co., Inc. | 3150 | 3150 | 0 | 2580 | 2580 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9681-25 | PROCUREMENT OF THREE (3) TANKS OF MAPP GAS AND ONE (1) CYLINDER OF R22 REFRIGERANT | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-29 | GOP | - | 12600 | 12600 | 0 | 11000 | 11000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9684-25 | PROCUREMENT OF VARIOUS ACCESSORIES FOR PRESSURE WASHER TO BE USED FOR CLEANING THE MOTOR VEHICLE SERVICES AT PMO NCR NORTH | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-10-10 | GOP | - | 5250 | 5250 | 0 | 4821.43 | 4821.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PROCUREMENT OF VARIOUS MATERIALS FOR 2025 YEAR-END THANKSGIVING CELEBRATION | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-15 | GOP | - | 15000 | 15000 | 0 | 8812.67 | 8812.67 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF VARIOUS MATERIALS FOR THE TREE PLANTING AND COASTAL CLEAN-UP ACTIVITY | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-01 | GOP | Kesco Industrial Sales Corporation | 5000 | 5000 | 0 | 4444 | 4444 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9933-25 | PROCUREMENT OF VARIOUS STAMP TO BE USED BY RECORDS UNIT | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-28 | N/A | N/A | N/A | 2025-12-26 | GOP | Jarin Art Sign & Gen. Mdse | 3450 | 3450 | 0 | 3450 | 3450 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PURCHASE OF OXYGEN REFILL FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-09-04 | GOP | - | 1800 | 1800 | 0 | 1651.79 | 1651.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
1-lot | PURCHASE OF PAINT AND VARIOUS MATERIALS FOR REPAINTING WORKS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-11-07 | GOP | - | 12000 | 12000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9753-25 | PURCHASE OF SEALANTS, WATERPROOFING AND VARIOUS CONSTRUCTION MATERIALS FOR THE EMERGENCY REPAIR OF DAMAGED ROOFING | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-19 | GOP | - | 15000 | 15000 | 0 | 14191.7 | 14191.7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9919-25 | PURCHASE OF STAINLESS STEEL DOORKNOBS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-12-17 | GOP | - | 3500 | 3500 | 0 | 2516 | 2516 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9767-25 | PURCHASE OF TWIN HOSE (OXYGEN-ACETYLENE) FOR VARIOUS STEEL REPAIRS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-08-24 | GOP | - | 4000 | 4000 | 0 | 2480.36 | 2480.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9565-25 | REPLACEMENT OF FAN RELAY AND SIDE MIRROR FOR HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-04-30 | GOP | - | 14350 | 14350 | 0 | 14350 | 14350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH-9564-25 | REPLACEMENT OF OIL FILTER, AIR FILTER, FUEL FILTER, CABIN FILTER FOR HYUNDAI STAREX YEAR MODEL 2018 WITH PLATE NO. NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-04-30 | GOP | - | 5750 | 5750 | 0 | 5750 | 5750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLY AND DELIVERY OF BATTERY FOR GENERATOR SET AT RS-2 CORREGIDOR ISLAND | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-05-05 | GOP | Batparts Supply Co., Inc. | 10000 | 10000 | 0 | 7130 | 7130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1-lot | PURCHASE OF PAINT AND VARIOUS MATERIALS FOR REPAINTING WORKS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-07 | GOP |  | 12000 | 12000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9640-25 | SUPPLY AND DELIVERY OF POWER SUPPLY UNIT (PSU) SEMI MODULAR 80 PLUS BRONZE 650 WATTS | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-03 | GOP | - | 4000 | 4000 | 0 | 2900 | 2900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Petty Cash
NH-9445-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9429-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-20 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9419-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9427-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-20 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | GOP |  | 600 | 600 | 0 | 350 | 350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9438-25 | Wheel Rubber and Bolt & Nut | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | GOP |  | 1740 | 1740 | 0 | 1553.57 | 1553.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9428-25 | Tire Mounting and Tire Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | GOP |  | 3250 | 3250 | 0 | 2901.79 | 2901.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9456-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9488-25 | Vulcanizing Flat Tire | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9497-25 | Cross joint Innova & Center Bearing Assembly | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | GOP |  | 9500 | 9500 | 0 | 9500 | 9500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9464-25 | Injection Pump Calibration | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | GOP |  | 11050 | 11050 | 0 | 11050 | 11050 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire - SND 2280, SLG 382 and SAB 4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | GOP |  | 2200 | 2200 | 0 | 2187.49 | 2187.49 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair and maintenance of service vehicle (Hyundai Starex 2017 with Plate no NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | GOP |  | 17946.43 | 17946.43 | 0 | 17946.43 | 17946.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9587-25 | For vulcanizing flat tire Toyota Hlux Plate No SND-2280 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | GOP |  | 1200 | 1200 | 0 | 1071.43 | 1071.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH=9642-25 | For use of Toyota Grandia with Plate No SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | GOP |  | 1200 | 1200 | 0 | 1071.43 | 1071.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9576-25 | For vulcanizing flat tire Toyota Grandia Plat e No SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9614-25 | For vulcanizing flat tire Toyota Commuter Plate No. SND-2264 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Hilux SNJ-2946 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 500 | 500 | 0 | 446.43 | 446.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9661-25 | Vulcanizing Flat Tire Hyundai Starex NOW 832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-07 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9721-25 | Break Cleaner For Toyota Innova Temp Plate 030806 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-30 | GOP |  | 600 | 600 | 0 | 562.5 | 562.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9701-25 | Auxillary Power Relay Fuse 95225-38050 120v 10/20 AMP | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-08 | GOP |  | 6000 | 6000 | 0 | 5357.14 | 5357.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire HONDA CRV NDJ 9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-08 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9889-25 | Alternator Pulley, Carbon Brush Holder Assy For Honda CRV NDJ 9510 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 | GOP |  | 5500 | 5500 | 0 | 4700 | 4700 | 0 | 5205.36 | [6 empty] | PETTY CASH
NH-9763-25 | Flasher Realy Assy For Hyundai Grand Starex with Plate No NOW 832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-24 | GOP |  | 3500 | 3500 | 0 | 3125 | 3125 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Toyota Grandia SAB-4357 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Vulcanizing Flat Tire Hyundai Starex NOW-892 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 1000 | 1000 | 0 | 835.71 | 835.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9937-25 | Vulcanizing Flat Tire - Hyundai Starex Plate No NOW-832 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-12 | GOP |  | 600 | 600 | 0 | 600 | 600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9899-25 | Head Light Bulb Hyudai Starex NBC-6114 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-04 | GOP |  | 600 | 600 | 0 | 535.71 | 535.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Replacement for Defective Battery - 3SMF N70 Engine Battery | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | GOP |  | 10000 | 10000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9437-25 | Repair and Maintenance of Phorocopier HP Copier Model E72630dn - 1 pc ADF Pick-up Assembly, 1 pc Laser Scanning Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | GOP |  | 15000 | 15000 | 0 | 12410.71 | 12410.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9439-25 | Repair and Maintenance of Various ACU NCR North - Copper Tube, Copper Elbow 2 pcs, Copper Coupling 2 pcs | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | GOP |  | 3620 | 3620 | 0 | 3232.14 | 3232.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9468-25 | Maintenance of sound system and ACU's board - Contact Cleaner Oil | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | GOP |  | 1000 | 1000 | 0 | 875 | 875 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9551-25 | Repair of ACU - Refrigerant, Access Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | GOP |  | 7500 | 7500 | 0 | 6696.43 | 6696.43 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9634-25 | Repair and replacement defective spare parts pressure washer. | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | GOP |  | 1000 | 1000 | 0 | 892.86 | 892.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair of ACU - Dual Capacitor | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | GOP |  | 1000 | 1000 | 0 | 848.21 | 848.21 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repairing of ACU located at entrance lobby PPA NCR North - Pressure Switch & MAPP Gas | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 2767.86 | 2767.86 | 0 | 2767.86 | 2767.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Repair and maintenance of Comfort Room located at PWD and Men CR Lobby area - Bidet/Tank Lever/Lavatory/Faucet/Teflon | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 1392.86 | 1392.86 | 0 | 1392.86 | 1392.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| PSU Semi Modular 80 plus Bronze 650 Watts | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | GOP |  | 3000 | 3000 | 0 | 2589.29 | 2589.29 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| One set Circuit Breaker 50AMP | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-29 | GOP |  | 4000 | 4000 | 0 | 3750 | 3750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Lock | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-21 | GOP |  | 2000 | 2000 | 0 | 1740 | 1740 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9857-25 | Unit Contractor Switch relay 40 amp - 3rd flr acu | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-29 | GOP |  | 2500 | 2500 | 0 | 2500 | 2500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9540-25 | Paper Cup and Wooden Spoon | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 1178.57 | 1178.57 | 0 | 1178.57 | 1178.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9583-25 | Zonrox, Powder Soap | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | GOP |  | 520 | 520 | 0 | 429.24 | 429.24 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9561-25 | 2-Way Angle Valve | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | GOP |  | 500 | 500 | 0 | 280 | 280 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9619-25 | USB Microphone DCM 001U DC 4,5 | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-30 | GOP |  | 2000 | 2000 | 0 | 1116.07 | 1116.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9776-25 | Plastic Trash Bag (Medium, XL) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-25 | GOP |  | 6000 | 6000 | 0 | 5000 | 5000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9792-25 | Repair of Customer Feedback Surevey Box | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-15 | GOP |  | 1000 | 1000 | 0 | 1000 | 1000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9788-25 | Glue Board | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 | GOP |  | 2000 | 2000 | 0 | 1990 | 1990 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9794-25 | Green and Blue Plastic Celophane - National Maritime Weeek | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 | GOP |  | 780 | 780 | 0 | 780 | 780 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9960-25 | Nylon Rope | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-26 | GOP |  | 80 | 80 | 0 | 80 | 80 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9677-25 | Keybox Holder | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-07 | GOP |  | 3000 | 3000 | 0 | 2008.04 | 2008.04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| ISO Standards Manuals | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-06 | GOP |  | 1160 | 1160 | 0 | 1160 | 1160 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Three (3) pcs Certificate Frames | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-24 | GOP |  | 1000 | 1000 | 0 | 650 | 650 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9436-25 | Reinassance Laid Paper 8 1/2x13 White 100gsm | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | GOP |  | 3250 | 3250 | 0 | 2678.57 | 2678.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9470-25 | Automatic numbering stamp for used of Cashiering Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | GOP |  | 2000 | 2000 | 0 | 1784.82 | 1784.82 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9528-25 | Automatic numbering stamp for used of Cashiering Unit | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | GOP |  | 2000 | 2000 | 0 | 1867.86 | 1867.86 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Cash Box, Mouse Trap and Mouse Sticky Trap | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | GOP |  | 4000 | 4000 | 0 | 2433.04 | 2433.04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9481-25 | Three (3) pcs Rubber Stamp | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | GOP |  | 2250 | 2250 | 0 | 2250 | 2250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9529-25 | Rubber Stamp | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | GOP |  | 800 | 800 | 0 | 800 | 800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9529-25 | Two (2) pcs Certificate Holder | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | GOP |  | 300 | 300 | 0 | 260 | 260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9530-25 | Two (2) pcs Frames | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | GOP |  | 300 | 300 | 0 | 260 | 260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9548-25 | Corkboard | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | GOP |  | 2000 | 2000 | 0 | 1651.79 | 1651.79 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9590-25 | Pilot Hi-Techpoint 07 RT - Blue | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | GOP |  | 3000 | 3000 | 0 | 2057.14 | 2057.14 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9723-25 | Double Mounting Tape | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-06 | GOP |  | 4750 | 4750 | 0 | 4241.07 | 4241.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9649-25 | Dater and Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | GOP |  | 2900 | 2900 | 0 | 2303.57 | 2303.57 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9783-25 | Dater and Stamping Machine | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | GOP |  | 2000 | 2000 | 0 | 1991.07 | 1991.07 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9726-25 | Vellum Board | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-12 | GOP |  | 3000 | 3000 | 0 | 660.71 | 660.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9643-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | GOP |  | 750 | 750 | 0 | 615.18 | 615.18 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
| Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | GOP |  | 100 | 100 | 0 | 100 | 100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9644-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | GOP |  | 2040 | 2040 | 0 | 1930.71 | 1930.71 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9648-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | GOP |  | 3745 | 3745 | 0 | 3544.38 | 3544.38 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9657-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | GOP |  | 878 | 878 | 0 | 830.96 | 830.96 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9658-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | GOP |  | 380 | 380 | 0 | 359.64 | 359.64 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9662-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-02 | GOP |  | 116 | 116 | 0 | 116 | 116 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9690-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-08 | GOP |  | 390 | 390 | 0 | 369.11 | 369.11 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9671-25 | Oxygen | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-11 | GOP |  | 1000 | 1000 | 0 | 520.54 | 520.54 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9689-25 | Acetylene | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-11 | GOP |  | 2000 | 2000 | 0 | 1750.89 | 1750.89 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9696-25 | Oxygen | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-17 | GOP |  | 600 | 600 | 0 | 520.54 | 520.54 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9724-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-12 | GOP |  | 915 | 915 | 0 | 865.98 | 865.98 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9733-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-13 | GOP |  | 180 | 180 | 0 | 180 | 180 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9747-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-15 | GOP |  | 230 | 230 | 0 | 230 | 230 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9789-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 | GOP |  | 795 | 795 | 0 | 752.41 | 752.41 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9811-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-17 | GOP |  | 285 | 285 | 0 | 285 | 285 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9816-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1901-01-31 | GOP |  | 420 | 420 | 0 | 397.5 | 397.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9817-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-25 | GOP |  | 170 | 170 | 0 | 170 | 170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9822-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | GOP |  | 50 | 50 | 0 | 50 | 50 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9828-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-02 | GOP |  | 300 | 300 | 0 | 300 | 300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9835-25 | Construction Materials | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-13 | GOP |  | 997.5 | 997.5 | 0 | 944.06 | 944.06 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
NH-9682-25 | PROCUREMENT OF TWENTY-FIVE (25) PACKS OF FOLDER DIVIDER (A4),TWENTY-FIVE (25) PACKS OF FOLDER DIVER (LEGAL), ELEVEN (11) PACKS OF PLASTIC SLIDING FOLDER (CLEAR), ONE (1) REAM OF COLORED PAPER (ASSORTED COLOR) AND TWO (2) PACKS OF STICKER PAPER (GLOSSY) | PMO-NCR North | Sec. 32 Direct Acquisition | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2025-07-31 | GOP | - | 6000 | 6000 | 0 | 3580 | 3580 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PETTY CASH
Total Allotted Budget of Procurement Activities | [18 empty] | 10307842.82
Total Contract Price of Procurement Activities Conducted | [18 empty] | 9015500.6
Total Savings(Total Alloted Budget - Total Contract Price | [18 empty] | 1292342.22
| Prepared by: |  |  |  | Reviewed by: | [9 empty] | Recommending Approval: | [10 empty] | Noted by: | [6 empty] | Recommending Approval: | Noted by:
| JEYMER M. SELOSA |  |  |  | MARISA T. ARIMADO | [9 empty] | FRANCIS ALDRICH A. RUBIO | [10 empty] | JENNELIZA D. REBONG | [6 empty] | FRANCIS ALDRICH A. RUBIO | JENNELIZA D. REBONG
| BAC , Support Staff |  |  |  | BAC Secretariat, Head | [9 empty] | BAC-NCRN Chairperson | [10 empty] | Port Manager / Head of Procuring Entity | [6 empty] | BAC-NCRN Chairperson | Port Manager / Head of Procuring Entity

## Sheet1
Supply and Delivery of Heavy Duty Paper Shredder | 39000 | 29250
Supply and Delivery of Ink Tank Printer | 40000 | 33632
Supply and Delivery of Printer, Dot matrix, LX310 | 45000 | 42900
Supply and Delivery of UPS 800VA | 45000 | 44500
Supply and Delivery of External Portable Drive 2TB | 12000 | 9768
Supply and Delivery of Bill Counting Machine and UV Counterfeit Money Detector | 30000 | 18000
Supply and Delivery of Dashboard Camera | 20000 | 19500
Supply and Delivery of Search Light | 5000 | 0
Supply and Delivery of Compact Camera with 30x Optical Zoom | 50000 | 0
| 286000 | 197550
88450
38450